## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Milestone 1 | US-01 | As a researcher, I want to enter a product description so that the system can generate relevant synthetic users. | Must Have | None | Akula Nikitha | Completed
Milestone 1 | US-02 | As a researcher, I want to enter a target audience so that personas match the intended customer group. | Must Have | US-01 | Akula Nikitha | Completed
Milestone 1 | US-03 | As a researcher, I want to enter a research objective so that the generated personas support my research goal. | Must Have | US-01, US-02 | Akula Nikitha | Completed
Milestone 2 | US-04 | As a researcher, I want a backend service to generate synthetic personas so that I can receive persona data automatically. | Must Have | US-01, US-02, US-03 | Akula Nikitha | Completed
Milestone 2 | US-05 | As a researcher, I want the system to generate multiple personas so that I can test different customer profiles. | Must Have | US-04 | Akula Nikitha | Completed
Milestone 2 | US-06 | As a researcher, I want to choose the number of personas so that I can generate the required sample size. | Must Have | US-05 | Akula Nikitha | Completed
Milestone 3 | US-07 | As a researcher, I want detailed persona attributes such as age, gender, location, income, interests, and buying behavior so that I can analyze customers more deeply. | Must Have | US-04, US-05 | Akula Nikitha | Completed
Milestone 3 | US-08 | As a researcher, I want each persona to have a goal and bio so that the persona is easier to understand and use in research. | Should Have | US-07 | Akula Nikitha | Completed
Milestone 3 | US-09 | As a researcher, I want the frontend to display generated personas clearly so that I can review the results easily. | Must Have | US-04, US-07 | Akula Nikitha | Completed
Milestone 3 | US-10 | As a researcher, I want frontend and backend API integration so that generated persona data appears in the application. | Must Have | US-04, US-09 | Akula Nikitha | Completed
Milestone 4 | US-11 | As a researcher, I want AI/LLM-based persona generation so that personas are more realistic and context-aware. | Could Have | US-07, US-10 | Akula Nikitha | Completed
Milestone 4 | US-12 | As a researcher, I want advanced research insights and improved validation so that generated personas can support deeper analysis. | Could Have | US-11 | Akula Nikitha | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-01 | T-01 | Create product description input field |  |  | Akula Nikitha | Frontend | Completed | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-02 | Create target audience input field |  |  | Akula Nikitha | Frontend | Completed | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-03 | Create research objective input field |  |  | Akula Nikitha | Frontend | Completed | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-04 | Create FastAPI backend endpoint for persona generation |  |  | Akula Nikitha | Backend | Completed | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-05 | Implement multiple persona generation logic |  |  | Akula Nikitha | Backend | Completed | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-06 | Connect persona count selection to API request |  |  | Akula Nikitha | Frontend/API | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-07 | Add detailed persona attributes to backend response |  |  | Akula Nikitha | Backend | Completed | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-08 | Add persona goal and bio fields |  |  | Akula Nikitha | Backend | Completed | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-09 | Build persona cards and display generated fields |  |  | Akula Nikitha | Frontend | Completed | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-10 | Integrate React frontend with FastAPI endpoint |  |  | Akula Nikitha | Frontend/API | Completed | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-11 | Test API response and frontend rendering |  |  | Akula Nikitha | Testing | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-12 | Integrate LLM/AI-based persona generation |  |  | Akula Nikitha | AI/Backend | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
US-12 | T-13 | Implement advanced insights and validation |  |  | Akula Nikitha | Research/Backend | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Milestone 1 | Day 1 | No known impediment recorded. | Continued development of the initial frontend inputs.
Milestone 2 | Day 1 | Backend and frontend integration required testing. | Tested the FastAPI endpoint through Swagger and connected the frontend request.
Milestone 3 | Day 1 | Persona fields needed to be expanded and displayed correctly. | Added detailed persona attributes including goal and bio and tested the API response.
Milestone 3 | Day 2 | Frontend JSX/layout issues occurred during UI updates. | Corrected duplicated JSX blocks, missing closing tags, and rendering structure.
Milestone 4 | Day 1 | AI/LLM integration and advanced research features required final testing. | Completed AI/LLM-based persona generation, research insights, product validation, and final workflow testing.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Milestone 1 |  |  | Akula Nikitha | Continue building the core frontend inputs and project structure. | Avoid delaying API planning until the UI is complete. | Incremental development and testing. | Continue with backend implementation.
2 | Milestone 2 |  |  | Akula Nikitha | Test backend endpoints using Swagger before frontend integration. | Avoid changing backend and frontend simultaneously without testing. | Small, testable implementation steps. | Use API testing before UI debugging.
3 | Milestone 3 |  | 10th | Akula Nikitha | Continue detailed persona generation and API testing. | Avoid duplicating JSX blocks or making large untested UI changes. | Incremental frontend/backend integration. | Keep testing after each major change.
4 | Milestone 4 |  | Continue improving AI/LLM persona generation, research insights, and product validation. | Avoid relying on untested AI outputs or leaving final integration issues unresolved. | Continue end-to-end testing, API validation, and structured research outputs. | Carry future enhancements such as persistent storage, authentication, and richer analytics into the next phase. | Document actual progress and remaining work. | Carry incomplete AI/advanced-insight work into the next milestone.
5
6
7

## Project Notes
Synthetic User Generation Platform - Agile Notes
Current status | Core generation, interviews, insights, validation, and report workflow developed.
Final PDF task | Fix report formatting and reduce report length by using a compact persona overview and detailed interviewed profiles.
Demo workflow | Generate Personas -> Persona Survey -> Extract Insights -> Product Validation -> Research Report
Recommended live demo | 5 personas, 3 interviewed personas
Important | Exact team-member names and sprint dates were not supplied, so existing workbook values were not replaced with invented names or dates.